## Jan 2026
BARODA MOULDS AND DIES - JAN'2026
Deliverable Distribution Table & Man-days Estimation Plan (DDT - ME)
|  |  | MLS | [5 empty] | SPM |  |  |  | SK |  |  |  | HMS
Sr. No. | Deliverable | Priority | Plan |  | Actual |  | Actual |  | Plan |  | Actual |  | Plan |  | Actual |  | Plan |  | Actual
|  |  | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site
1 | To prepare and share week-wise Production, Rejection and OTD data for both units (BMD 1 and 2) | [7 empty] | 2 | 0.5 |  |  | 2 | 1 |  |  | 2 | 3
2 | To conduct a weekly mixing audit at BMD unit 2 | [7 empty] | 2 | 0.5 |  |  | 4 | 4 |  |  | 4 | 4
3 | To prepare Dec'25 Load planning Sheet | [11 empty] | 4 |  |  |  | 4
4 | To prepare the Rolling Nov'25 Load planning sheet | [7 empty] | 4 |  |  |  | 4 |  |  |  | 4
5 | To take follow-up of Daily Plan vs Actual report | [16 empty] | 1
6 | To Daily Analyse the Daily plan vs Actual Report and update the cumulative summary sheet |  |  | 2 | [5 empty] | 3 |  |  |  | 3 |  |  |  | 8
7 | To prepare an Objective sheet, including the Sales, ITR, OTD, etc | [8 empty] | 0.25 |  |  |  | 1 |  |  | 1
8 | To discuss and finalize the MRM structure |  |  | 0.5 |  |  |  |  | 1.5 | 0.5 |  |  |  | 0.5 |  |  | 1.5 | 1.5
9 | To conduct the Monthly review meeting with Arvind Sir |  | 3 | [5 empty] | 12 | 1 |  |  | 3 | 2 |  |  | 8
10 | Collect the current available FMEA and HIRA sheet and understand the sheet for APG | [7 empty] | 1 | 0.5 |  |  | 3 | 0.5 |  |  | 1 | 0.5
11 | Prepare SBS sheet for APG dept. as per required skills | [7 empty] | 0.5 | 0.5 |  |  | 0.5 | 1.5 |  |  | 0.5 | 3
12 | Skill Mapping of the APG dept. team members | [11 empty] | 1
13 | Prepare textual OPLs for APG | [8 empty] | 0.5 |  |  |  | 0.5 |  |  |  | 3.5
14 | Get the textual OPLs validated for APG by Arvind sir/ Rajesh sir | [11 empty] | 0.5
15 | Conduct trainings of 2 batches for APG team members with test papers | [7 empty] | 2 | 0.25 |  |  | 2 | 0.5 |  |  | 4 | 1.5
16 | Collect photos for APG for preparing Photographic OPLs | [8 empty] | 0.5 |  |  |  | 0.5 |  |  | 2 | 1
17 | Prepare Photograhpic OPL for APG |  |  | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 3
18 | Get the photographic OPLs validated for APG by Arvind sir/ Rajesh sir | [11 empty] | 0.5 |  |  |  | 0.5
19 | Coordinate with BMD team and get magnetic board for displaying the posters | [11 empty] | 0.25
20 | Display the photographic OPLs near the APG area | [15 empty] | 0.5
21 | To collect current available formats & documents of ISO 9K, 14K and 45K at Unit-1 | [15 empty] | 1 | 0.5
22 | To verify the format filling status of formats and documents of ISO 9K, 14K and 45K at Unit-1 | [7 empty] | 3 | [7 empty] | 3
23 | To Update & Share the required formats to the required department team members of Unit-2 as per ISO 9K, 14K and 45K | [8 empty] | 0.25 |  |  | 4 | 0.25 |  |  | 4 | 2
24 | To Take follow-up of Machine Installation Action Plan of Unit-2 | [11 empty] | 1 |  |  |  | 1 | 0.5
25 | To Conduct Training of Staff team members on:- - Train the Trainer - Internal Auditor's training on ISO 9K, 14K, 45K - Leadership Score - DMAIC - 8D Process, Customer Complaint |  | 4 | 0.5 |  |  |  |  | 4 | 1 |  |  | 4 | 1 |  |  | 4 | 2
Total Hours |  |  | 7 | 4 | 0 | 0 | 0 | 0 | 32 | 10.25 | 0 | 0 | 33.75 | 17.25 | 0 | 0 | 46 | 35 | #REF! | #REF!
Total Man-days |  |  | 1.1667 | 0.53333 | 0 | 0 | 0 | 0 | 5.3333 | 1.3667 | 0 | 0 | 5.625 | 2.3 | 0 | 0 | 7.6667 | 4.6667 | #REF! | #REF!
Total BMD Man Days |  |  | 1.7 |  | 0 |  | 0 |  | 6.7 |  | 0 |  | 7.925 |  | 0 |  | 12.3333 |  | #REF!
Fixed Tasks / other task |  |  | MLS | [5 empty] | SPM |  |  |  | SK
|  |  | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site
1 | Monthly Deliverables Planning with DDT-ME (Including Click up Updation) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 | 3 |  |  | 0 | 2
2 | Monthly Review PPT |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 3
3 | Invoice |  | 0 | 0 |  |  |  |  | 0 | 0.5 |  |  | 0 | 0.5 |  |  | 0 | 1.5
4 | MCTC |  | 0 | 0 |  |  |  |  | 0 | 0.5 |  |  | 0 | 0.5 |  |  | 0 | 0.5
5 | RC7 (Including Realignment of Deliverables) (0.5 * 8) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 1
6 | Fortnightly and Monthly Review with Internal team - QA&QC (Including Preparation time) |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
7 | Agenda and Action Plan Preparation for visits (6*0.25) and (6*1) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 4
8 | Daily Mail checking and Click up updation Activity |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0.5 |  |  | 0 | 0.5
9 | Review of Master list of Action Plan and take the follow-up for the same and Weekly RYG (4*1.5) |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0.5 |  |  | 0 | 0.5
10 | Data Sync |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
Total Hours Fix |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 13 | 0 | 0
Total Man-days Fix |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53333 | 0 | 0 | 0 | 0.66667 | 0 | 0 | 0 | 1.7333 | 0 | 0
Total BMD Man Days Fix |  |  | 0 |  | 0 |  | 0 |  | 0.53333 |  | 0 |  | 0.66667 |  | 0 |  | 1.7333 |  | 0
Grand Total Hours |  |  | 7 | 4 | 0 | 0 | 0 | 0 | 32 | 14.25 | 0 | 0 | 33.75 | 22.25 | 0 | 0 | 46 | 48 | #REF! | #REF!
Grand Total Man-days |  |  | 1.1667 | 0.53333 | 0 | 0 | 0 | 0 | 5.3333 | 1.9 | 0 | 0 | 5.625 | 2.9667 | 0 | 0 | 7.6667 | 6.4 | #REF! | #REF!
Grand Total BMD Man Days |  |  | 1.7 |  | 0 |  | 0 |  | 7.2333 |  | 0 |  | 8.5917 |  | 0 |  | 14.0667 |  | #REF!
Other Company Man Days | [18 empty] | 0 | 0
Other Company's Total Man Days | [18 empty] | 0
Total Man Days |  |  | 1.7 |  | 0 |  | 0 |  | 7.2333 |  | 0 |  | 8.5917 |  | 0 |  | 14.0667 |  | #REF!
Total Available Man Days |  |  | 24 |  |  |  | 25 |  | 24 |  | 25 |  | 24 |  | 25 |  | 24 |  | 21
Total Planned Leave |  |  |  |  | 21 |  | 21 |  |  |  | 21 |  |  |  | 21 |  |  |  | 21
Total buffer Man Days |  |  | 22.3 |  | -21 |  | 4 |  | 16.7667 |  | 4 |  | 15.4083 |  | 4 |  | 9.9333 |  | #REF!
Note on N53: Shashank: 2 Days - Shrenik Audit 2 Days - Labtech

## Feb 2026
BARODA MOULDS AND DIES - FEB'2026
Deliverable Distribution Table & Man-days Estimation Plan (DDT - ME)
|  |  | MLS | [5 empty] | SPM |  |  |  | SK |  |  |  | HMS
Sr. No. | Deliverable | Priority | Plan |  | Actual |  | Actual |  | Plan |  | Actual |  | Plan |  | Actual |  | Plan |  | Actual
|  |  | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site
1 | To prepare and share week-wise Production, Rejection and OTD data for both units (BMD 1 and 2) | [7 empty] | 2 | 0.5 |  |  | 2 | 1 |  |  | 2 | 3
2 | To conduct a weekly mixing audit at BMD unit 2 | [7 empty] | 2 | 0.5 |  |  | 4 | 4 |  |  | 4 | 4
3 | To prepare Dec'25 Load planning Sheet | [11 empty] | 4 |  |  |  | 4
4 | To prepare the Rolling Nov'25 Load planning sheet | [7 empty] | 4 |  |  |  | 4 |  |  |  | 4
5 | To take follow-up of Daily Plan vs Actual report | [16 empty] | 1
6 | To Daily Analyse the Daily plan vs Actual Report and update the cumulative summary sheet |  |  | 2 | [5 empty] | 3 |  |  |  | 3 |  |  |  | 8
7 | To prepare an Objective sheet, including the Sales, ITR, OTD, etc | [8 empty] | 0.25 |  |  |  | 1 |  |  | 1
8 | To discuss and finalize the MRM structure |  |  | 0.5 |  |  |  |  | 1.5 | 0.5 |  |  |  | 0.5 |  |  | 1.5 | 1.5
9 | To conduct the Monthly review meeting with Arvind Sir |  | 3 | [5 empty] | 12 | 1 |  |  | 3 | 2 |  |  | 8
10 | Collect the current available FMEA and HIRA sheet and understand the sheet for APG | [7 empty] | 1 | 0.5 |  |  | 3 | 0.5 |  |  | 1 | 0.5
11 | Prepare SBS sheet for APG dept. as per required skills | [7 empty] | 0.5 | 0.5 |  |  | 0.5 | 1.5 |  |  | 0.5 | 3
12 | Skill Mapping of the APG dept. team members | [11 empty] | 1
13 | Prepare textual OPLs for APG | [8 empty] | 0.5 |  |  |  | 0.5 |  |  |  | 3.5
14 | Get the textual OPLs validated for APG by Arvind sir/ Rajesh sir | [11 empty] | 0.5
15 | Conduct trainings of 2 batches for APG team members with test papers | [7 empty] | 2 | 0.25 |  |  | 2 | 0.5 |  |  | 4 | 1.5
16 | Collect photos for APG for preparing Photographic OPLs | [8 empty] | 0.5 |  |  |  | 0.5 |  |  | 2 | 1
17 | Prepare Photograhpic OPL for APG |  |  | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 3
18 | Get the photographic OPLs validated for APG by Arvind sir/ Rajesh sir | [11 empty] | 0.5 |  |  |  | 0.5
19 | Coordinate with BMD team and get magnetic board for displaying the posters | [11 empty] | 0.25
20 | Display the photographic OPLs near the APG area | [15 empty] | 0.5
21 | To collect current available formats & documents of ISO 9K, 14K and 45K at Unit-1 | [15 empty] | 1 | 0.5
22 | To verify the format filling status of formats and documents of ISO 9K, 14K and 45K at Unit-1 | [7 empty] | 3 | [7 empty] | 3
23 | To Update & Share the required formats to the required department team members of Unit-2 as per ISO 9K, 14K and 45K | [8 empty] | 0.25 |  |  | 4 | 0.25 |  |  | 4 | 2
24 | To Take follow-up of Machine Installation Action Plan of Unit-2 | [11 empty] | 1 |  |  |  | 1 | 0.5
25 | To Conduct Training of Staff team members on:- - Train the Trainer - Internal Auditor's training on ISO 9K, 14K, 45K - Leadership Score - DMAIC - 8D Process, Customer Complaint |  | 4 | 0.5 |  |  |  |  | 4 | 1 |  |  | 4 | 1 |  |  | 4 | 2
Total Hours |  |  | 7 | 4 | 0 | 0 | 0 | 0 | 32 | 10.25 | 0 | 0 | 33.75 | 17.25 | 0 | 0 | 46 | 35 | #REF! | #REF!
Total Man-days |  |  | 1.1667 | 0.53333 | 0 | 0 | 0 | 0 | 5.3333 | 1.3667 | 0 | 0 | 5.625 | 2.3 | 0 | 0 | 7.6667 | 4.6667 | #REF! | #REF!
Total BMD Man Days |  |  | 1.7 |  | 0 |  | 0 |  | 6.7 |  | 0 |  | 7.925 |  | 0 |  | 12.3333 |  | #REF!
Fixed Tasks / other task |  |  | MLS | [5 empty] | SPM |  |  |  | SK
|  |  | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site
1 | Monthly Deliverables Planning with DDT-ME (Including Click up Updation) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 | 3 |  |  | 0 | 2
2 | Monthly Review PPT |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 3
3 | Invoice |  | 0 | 0 |  |  |  |  | 0 | 0.5 |  |  | 0 | 0.5 |  |  | 0 | 1.5
4 | MCTC |  | 0 | 0 |  |  |  |  | 0 | 0.5 |  |  | 0 | 0.5 |  |  | 0 | 0.5
5 | RC7 (Including Realignment of Deliverables) (0.5 * 8) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 1
6 | Fortnightly and Monthly Review with Internal team - QA&QC (Including Preparation time) |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
7 | Agenda and Action Plan Preparation for visits (6*0.25) and (6*1) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 4
8 | Daily Mail checking and Click up updation Activity |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0.5 |  |  | 0 | 0.5
9 | Review of Master list of Action Plan and take the follow-up for the same and Weekly RYG (4*1.5) |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0.5 |  |  | 0 | 0.5
10 | Data Sync |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
Total Hours Fix |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 13 | 0 | 0
Total Man-days Fix |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53333 | 0 | 0 | 0 | 0.66667 | 0 | 0 | 0 | 1.7333 | 0 | 0
Total BMD Man Days Fix |  |  | 0 |  | 0 |  | 0 |  | 0.53333 |  | 0 |  | 0.66667 |  | 0 |  | 1.7333 |  | 0
Grand Total Hours |  |  | 7 | 4 | 0 | 0 | 0 | 0 | 32 | 14.25 | 0 | 0 | 33.75 | 22.25 | 0 | 0 | 46 | 48 | #REF! | #REF!
Grand Total Man-days |  |  | 1.1667 | 0.53333 | 0 | 0 | 0 | 0 | 5.3333 | 1.9 | 0 | 0 | 5.625 | 2.9667 | 0 | 0 | 7.6667 | 6.4 | #REF! | #REF!
Grand Total BMD Man Days |  |  | 1.7 |  | 0 |  | 0 |  | 7.2333 |  | 0 |  | 8.5917 |  | 0 |  | 14.0667 |  | #REF!
Other Company Man Days | [18 empty] | 0 | 0
Other Company's Total Man Days | [18 empty] | 0
Total Man Days |  |  | 1.7 |  | 0 |  | 0 |  | 7.2333 |  | 0 |  | 8.5917 |  | 0 |  | 14.0667 |  | #REF!
Total Available Man Days |  |  | 24 |  |  |  | 25 |  | 24 |  | 25 |  | 24 |  | 25 |  | 24 |  | 21
Total Planned Leave |  |  |  |  | 21 |  | 21 |  |  |  | 21 |  |  |  | 21 |  |  |  | 21
Total buffer Man Days |  |  | 22.3 |  | -21 |  | 4 |  | 16.7667 |  | 4 |  | 15.4083 |  | 4 |  | 9.9333 |  | #REF!
Note on N53: Shashank: 2 Days - Shrenik Audit 2 Days - Labtech

## March 2026
BARODA MOULDS AND DIES - FEB'2026
Deliverable Distribution Table & Man-days Estimation Plan (DDT - ME)
|  |  | MLS | [5 empty] | SPM |  |  |  | SK |  |  |  | HMS
Sr. No. | Deliverable | Priority | Plan |  | Actual |  | Actual |  | Plan |  | Actual |  | Plan |  | Actual |  | Plan |  | Actual
|  |  | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site
1 | To prepare and share week-wise Production, Rejection and OTD data for both units (BMD 1 and 2) | [7 empty] | 2 | 0.5 |  |  | 2 | 1 |  |  | 2 | 3
2 | To conduct a weekly mixing audit at BMD unit 2 | [7 empty] | 2 | 0.5 |  |  | 4 | 4 |  |  | 4 | 4
3 | To prepare Dec'25 Load planning Sheet | [11 empty] | 4 |  |  |  | 4
4 | To prepare the Rolling Nov'25 Load planning sheet | [7 empty] | 4 |  |  |  | 4 |  |  |  | 4
5 | To take follow-up of Daily Plan vs Actual report | [16 empty] | 1
6 | To Daily Analyse the Daily plan vs Actual Report and update the cumulative summary sheet |  |  | 2 | [5 empty] | 3 |  |  |  | 3 |  |  |  | 8
7 | To prepare an Objective sheet, including the Sales, ITR, OTD, etc | [8 empty] | 0.25 |  |  |  | 1 |  |  | 1
8 | To discuss and finalize the MRM structure |  |  | 0.5 |  |  |  |  | 1.5 | 0.5 |  |  |  | 0.5 |  |  | 1.5 | 1.5
9 | To conduct the Monthly review meeting with Arvind Sir |  | 3 | [5 empty] | 12 | 1 |  |  | 3 | 2 |  |  | 8
10 | Collect the current available FMEA and HIRA sheet and understand the sheet for APG | [7 empty] | 1 | 0.5 |  |  | 3 | 0.5 |  |  | 1 | 0.5
11 | Prepare SBS sheet for APG dept. as per required skills | [7 empty] | 0.5 | 0.5 |  |  | 0.5 | 1.5 |  |  | 0.5 | 3
12 | Skill Mapping of the APG dept. team members | [11 empty] | 1
13 | Prepare textual OPLs for APG | [8 empty] | 0.5 |  |  |  | 0.5 |  |  |  | 3.5
14 | Get the textual OPLs validated for APG by Arvind sir/ Rajesh sir | [11 empty] | 0.5
15 | Conduct trainings of 2 batches for APG team members with test papers | [7 empty] | 2 | 0.25 |  |  | 2 | 0.5 |  |  | 4 | 1.5
16 | Collect photos for APG for preparing Photographic OPLs | [8 empty] | 0.5 |  |  |  | 0.5 |  |  | 2 | 1
17 | Prepare Photograhpic OPL for APG |  |  | 1 | [5 empty] | 1 |  |  |  | 1 |  |  |  | 3
18 | Get the photographic OPLs validated for APG by Arvind sir/ Rajesh sir | [11 empty] | 0.5 |  |  |  | 0.5
19 | Coordinate with BMD team and get magnetic board for displaying the posters | [11 empty] | 0.25
20 | Display the photographic OPLs near the APG area | [15 empty] | 0.5
21 | To collect current available formats & documents of ISO 9K, 14K and 45K at Unit-1 | [15 empty] | 1 | 0.5
22 | To verify the format filling status of formats and documents of ISO 9K, 14K and 45K at Unit-1 | [7 empty] | 3 | [7 empty] | 3
23 | To Update & Share the required formats to the required department team members of Unit-2 as per ISO 9K, 14K and 45K | [8 empty] | 0.25 |  |  | 4 | 0.25 |  |  | 4 | 2
24 | To Take follow-up of Machine Installation Action Plan of Unit-2 | [11 empty] | 1 |  |  |  | 1 | 0.5
25 | To Conduct Training of Staff team members on:- - Train the Trainer - Internal Auditor's training on ISO 9K, 14K, 45K - Leadership Score - DMAIC - 8D Process, Customer Complaint |  | 4 | 0.5 |  |  |  |  | 4 | 1 |  |  | 4 | 1 |  |  | 4 | 2
Total Hours |  |  | 7 | 4 | 0 | 0 | 0 | 0 | 32 | 10.25 | 0 | 0 | 33.75 | 17.25 | 0 | 0 | 46 | 35 | #REF! | #REF!
Total Man-days |  |  | 1.1667 | 0.53333 | 0 | 0 | 0 | 0 | 5.3333 | 1.3667 | 0 | 0 | 5.625 | 2.3 | 0 | 0 | 7.6667 | 4.6667 | #REF! | #REF!
Total BMD Man Days |  |  | 1.7 |  | 0 |  | 0 |  | 6.7 |  | 0 |  | 7.925 |  | 0 |  | 12.3333 |  | #REF!
Fixed Tasks / other task |  |  | MLS | [5 empty] | SPM |  |  |  | SK
|  |  | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site
1 | Monthly Deliverables Planning with DDT-ME (Including Click up Updation) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 | 3 |  |  | 0 | 2
2 | Monthly Review PPT |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 3
3 | Invoice |  | 0 | 0 |  |  |  |  | 0 | 0.5 |  |  | 0 | 0.5 |  |  | 0 | 1.5
4 | MCTC |  | 0 | 0 |  |  |  |  | 0 | 0.5 |  |  | 0 | 0.5 |  |  | 0 | 0.5
5 | RC7 (Including Realignment of Deliverables) (0.5 * 8) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 1
6 | Fortnightly and Monthly Review with Internal team - QA&QC (Including Preparation time) |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
7 | Agenda and Action Plan Preparation for visits (6*0.25) and (6*1) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 4
8 | Daily Mail checking and Click up updation Activity |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0.5 |  |  | 0 | 0.5
9 | Review of Master list of Action Plan and take the follow-up for the same and Weekly RYG (4*1.5) |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0.5 |  |  | 0 | 0.5
10 | Data Sync |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
Total Hours Fix |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 13 | 0 | 0
Total Man-days Fix |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53333 | 0 | 0 | 0 | 0.66667 | 0 | 0 | 0 | 1.7333 | 0 | 0
Total BMD Man Days Fix |  |  | 0 |  | 0 |  | 0 |  | 0.53333 |  | 0 |  | 0.66667 |  | 0 |  | 1.7333 |  | 0
Grand Total Hours |  |  | 7 | 4 | 0 | 0 | 0 | 0 | 32 | 14.25 | 0 | 0 | 33.75 | 22.25 | 0 | 0 | 46 | 48 | #REF! | #REF!
Grand Total Man-days |  |  | 1.1667 | 0.53333 | 0 | 0 | 0 | 0 | 5.3333 | 1.9 | 0 | 0 | 5.625 | 2.9667 | 0 | 0 | 7.6667 | 6.4 | #REF! | #REF!
Grand Total BMD Man Days |  |  | 1.7 |  | 0 |  | 0 |  | 7.2333 |  | 0 |  | 8.5917 |  | 0 |  | 14.0667 |  | #REF!
Other Company Man Days | [18 empty] | 0 | 0
Other Company's Total Man Days | [18 empty] | 0
Total Man Days |  |  | 1.7 |  | 0 |  | 0 |  | 7.2333 |  | 0 |  | 8.5917 |  | 0 |  | 14.0667 |  | #REF!
Total Available Man Days |  |  | 24 |  |  |  | 25 |  | 24 |  | 25 |  | 24 |  | 25 |  | 24 |  | 21
Total Planned Leave |  |  |  |  | 21 |  | 21 |  |  |  | 21 |  |  |  | 21 |  |  |  | 21
Total buffer Man Days |  |  | 22.3 |  | -21 |  | 4 |  | 16.7667 |  | 4 |  | 15.4083 |  | 4 |  | 9.9333 |  | #REF!
Note on N53: Shashank: 2 Days - Shrenik Audit 2 Days - Labtech

## April 2026
BARODA MOULDS AND DIES - April'2026
Deliverable Distribution Table & Man-days Estimation Plan (DDT - ME)
|  |  | MLS | [5 empty] | SPM |  |  |  | SH
Sr. No. | Deliverable | Priority | Plan |  | Actual |  | Actual |  | Plan |  | Actual |  | Plan |  | Actual |  | Actual
|  |  | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site
1 | To Review all department formats & documents for Unit 1 | W1 | [6 empty] | 1 | 2.5 |  |  | 3 | 2 |  |  | 4
2 | To ensure error -free records for audit related Documents Unit 1 | W1 | [6 empty] | 1 | 0.5 |  |  | 4
3 | To set up proper folder structure & files preparation for external audit for easy traceability for Unit 1 | W2 | [6 empty] | 1 | 0.5 |  |  | 2 | 0.5
4 | To conduct training for staff on audit handling and questioning practice for Unit 1 | W2 | [6 empty] | 1 |  |  |  | 3
5 | To provide handholding support during external audit at Unit 1 | W2 | [6 empty] | 18 |  |  |  | 18
6 | To provide handholding support to Unit 1 team members for closing External audit NCs | W2 | [6 empty] | 2.5 | 0.5 |  |  | 5 | 1.5
7 | Review CAPA Format before submit to External audit site Unit 1 | W23 | [6 empty] | 1.5 |  |  |  | 1.5
8 | To prepare a training schedule and conduct training to Unit 2 team members. | W1 | [6 empty] | 2 |  |  |  | 4 | 0.5
9 | To take follow-up for poster & visuals and display support to Unit 2 | W12 | [7 empty] | 0.5 |  |  | 2 | 1
10 | To Review all department formats & documents for Unit 2 | W23 | [6 empty] | 1 | 2.5 |  |  | 3 | 2
11 | To ensure error -free records for audit related Documents Unit 2 | W3 | [6 empty] | 1 | 0.5 |  |  | 4
12 | To set up proper folder structure & files preparation for external audit for easy traceability for Unit 2 | W3 | [6 empty] | 1 | 0.5 |  |  | 2 | 0.5
13 | To conduct training for staff on audit handling and questioning practice for Unit 2 | W34 | [6 empty] | 1 |  |  |  | 3
14 | To provide handholding support during external audit at Unit 2 | W4 | [6 empty] | 12 |  |  |  | 12
15 | To provide handholding support to Unit 2 team members for closing External audit NCs | W45 | [6 empty] | 2.5 | 0.5 |  |  | 5 | 1.5
16 | Review CAPA Format before submit to External audit site Unit 2 | W5 | [6 empty] | 1.5 |  |  |  | 1.5
17 | To prepare Dec'25 Load planning Sheet | W12345 | [6 empty] | 1.5 |  |  |  | 1.5
18 | To take follow-up of Daily Plan vs Actual report | W12345 | [11 empty] | 3
19 | To Daily Analyse the Daily plan vs Actual Report and update the cumulative summary sheet | W12345 | [7 empty] | 0.5 |  |  |  | 8
20 | To conduct the Mid Monthly meeting with Arvind Sir | W3 | 3 | [5 empty] | 3 |  |  |  | 3
Total Hours |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 52.5 | 9 | 0 | 0 | 77.5 | 20.5 | 0 | 0 | #REF! | #REF!
Total Man-days |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 8.75 | 1.2 | 0 | 0 | 12.9167 | 2.7333 | 0 | 0 | #REF! | #REF!
Total BMD Man Days |  |  | 0.5 |  | 0 |  | 0 |  | 9.95 |  | 0 |  | 15.65 |  | 0 |  | #REF!
Fixed Tasks / other task |  |  | MLS | [5 empty] | SPM |  |  |  | SK
|  |  | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site
1 | Monthly Deliverables Planning with DDT-ME (Including Click up Updation) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 | 3 |  |  | 0 | 2
2 | Monthly Review PPT |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 3
3 | Invoice |  | 0 | 0 |  |  |  |  | 0 | 0.5 |  |  | 0 | 0.5 |  |  | 0 | 1.5
4 | MCTC |  | 0 | 0 |  |  |  |  | 0 | 0.5 |  |  | 0 | 0.5 |  |  | 0 | 0.5
5 | RC7 (Including Realignment of Deliverables) (0.5 * 8) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 1
6 | Fortnightly and Monthly Review with Internal team - QA&QC (Including Preparation time) |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
7 | Agenda and Action Plan Preparation for visits (6*0.25) and (6*1) |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 4
8 | Daily Mail checking and Click up updation Activity |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0.5 |  |  | 0 | 0.5
9 | Review of Master list of Action Plan and take the follow-up for the same and Weekly RYG (4*1.5) |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0.5 |  |  | 0 | 0.5
10 | Data Sync |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
Total Hours Fix |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 13
Total Man-days Fix |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53333 | 0 | 0 | 0 | 0.66667 | 0 | 0 | 0 | 1.7333
Total BMD Man Days Fix |  |  | 0 |  | 0 |  | 0 |  | 0.53333 |  | 0 |  | 0.66667 |  | 0 |  | 1.7333
Grand Total Hours |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 52.5 | 13 | 0 | 0 | 77.5 | 25.5 | 0 | 0 | #REF! | #REF!
Grand Total Man-days |  |  | 0.5 | 0 | 0 | 0 | 0 | 0 | 8.75 | 1.7333 | 0 | 0 | 12.9167 | 3.4 | 0 | 0 | #REF! | #REF!
Grand Total BMD Man Days |  |  | 0.5 |  | 0 |  | 0 |  | 10.4833 |  | 0 |  | 16.3167 |  | 0 |  | #REF!
Other Company Man Days | [16 empty] | 0 | 0
Other Company's Total Man Days | [16 empty] | 0
Total Man Days |  |  | 0.5 |  | 0 |  | 0 |  | 10.4833 |  | 0 |  | 16.3167 |  | 0 |  | #REF!
Total Available Man Days |  |  | 24 |  |  |  | 25 |  | 24 |  | 25 |  | 24 |  | 25 |  | 21
Total Planned Leave |  |  |  |  | 21 |  | 21 |  |  |  | 21 |  |  |  | 21 |  | 21
Total buffer Man Days |  |  | 23.5 |  | -21 |  | 4 |  | 13.5167 |  | 4 |  | 7.6833 |  | 4 |  | #REF!
Note on N48: Shashank: 2 Days - Shrenik Audit 2 Days - Labtech

## May 2026
Sr. No. | uvhj | Deliverable | Start Date | Target Date | Priority | Plan |  | Actual |  | Actual |  | Plan |  | Actual |  | Plan |  | Actual |  | Actual
1 | EHS | To revise EHS annexures and formats | 2026-05-01 | 2026-05-07 | W1 | [7 empty] | 1 |  |  |  | 2.5 |  |  | 4
2 | EHS | To follow up with Harish Bhai for reviewing EHS annexures and formats | 2026-05-01 | 2026-05-07 | W1 | [10 empty] | 2 | 0.5
3 | EHS | To prepare and discuss EHS objectives and MR-related activities | 2026-05-01 | 2026-05-16 | W2 | [6 empty] | 3 | 0.5 |  |  | 1 | 1
4 | EHS | To review HIRA points based on the applicability of Site 1 & site 2 | 2026-05-01 | 2026-05-16 | W2 | [6 empty] | 2 | 0.5 |  |  | 4 | 2
5 | EHS | To review and update the EHS procedure manual and EHS manual | 2026-05-01 | 2026-05-16 | W2 | [7 empty] | 3 |  |  |  | 16
6 | EHS | To review formats and supporting documents for gap identification | 2026-05-01 | 2026-05-16 | W2 | [6 empty] | 1 |  |  |  | 4
7 | EHS | To follow up on visual displays at Site 1 and Site 2 | 2026-05-01 | 2026-05-16 | W2 | [7 empty] | 0.5 |  |  | 1 | 0.5
8 | EHS | To follow up with Harish Bhai for the external audit date and schedule | 2026-05-01 | 2026-05-07 | W1 | [11 empty] | 1
9 | EHS | To create a centralized access folder for external audit readiness | 2026-05-01 | 2026-05-16 | W12 | [6 empty] | 1 |  |  |  | 2
10 | EHS | To provide EHS audit awareness training to all team members at Site 1 and Site 2 | 2026-05-16 | 2026-05-23 | W23 | [6 empty] | 2 |  |  |  | 4 | 0.5
11 | EHS | To prepare an audit checklist for conducting cross audits | 2026-05-16 | 2026-05-23 | W23 | [7 empty] | 0.5 |  |  |  | 2
12 | EHS | To conduct cross audits to identify and prevent maximum gaps before the external audit | 2026-05-16 | 2026-05-23 | W23 | [6 empty] | 4 | 0.5 |  |  | 4 | 0.5
13 | EHS | To prepare and share the audit report with Arvind Sir | 2026-05-16 | 2026-05-23 | W23 | [7 empty] | 1 |  |  |  | 3
14 | EHS | To provide handholding support during the EHS external audit | 2026-05-16 | 2026-05-23 | W23 | [6 empty] | 18 |  |  |  | 18
15 | EHS | To support BMD team members for external audit improvements and NC closure | 2026-05-01 | 2026-05-23 | W3 | [6 empty] | 3 |  |  |  | 3 | 1
16 | Rejection | To discuss & analyze past/ recent internal rejection parameters and review it with the chart papers for parameters compliance | 2026-05-01 | 2026-05-23 | W3 | [6 empty] | 2 |  |  |  | 2
17 | Rejection | To conduct process audits to verify rejection parameters | 2026-05-23 | 2026-05-31 | W345 | [7 empty] | 0.5 |  |  | 4 | 1
18 | Rejection | To analyze on collected process audit data on rejection parameters and prepare improvement plans | 2026-05-01 | 2026-05-31 | W5 | [6 empty] | 2 |  |  |  | 2 | 3
19 | SCM | To prepare the May'26 load planning sheet | 2026-05-01 | 2026-05-07 | W1 | [6 empty] | 0.5 |  |  |  | 1
20 | SCM | To follow up on the Daily Plan vs Actual report | 2026-05-01 | 2026-05-07 | W1 | [10 empty] | 1
21 | SCM | To analyze the Daily Plan vs Actual report and update the cumulative summary sheet | 2026-05-01 | 2026-05-31 | W12345 | [11 empty] | 1
22 | SCM | To conduct ROP compliance audit | 2026-05-01 | 2026-05-31 | W5 | [7 empty] | 0.5 |  |  | 2
23 | SCM | To conduct stock accuracy audit | 2026-05-01 | 2026-05-31 | W5 | [7 empty] | 0.5 |  |  | 2 | 0.5
24 | Review | To conduct the Mid Monthly meeting with Arvind Sir | 2026-05-01 | 2026-05-23 | W3 | 3 | [5 empty] | 3 |  |  |  | 3
Total Hours | [5 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 41.5 | 9 | 0 | 0 | 60 | 36 | 0 | 0 | #REF! | #REF!
Total Man-days | [5 empty] | 0.5 | 0 | 0 | 0 | 0 | 0 | 6.9167 | 1.2 | 0 | 0 | 10 | 4.8 | 0 | 0 | #REF! | #REF!
Total BMD Man Days | [5 empty] | 0.5 |  | 0 |  | 0 |  | 8.1167 |  | 0 |  | 14.8 |  | 0 |  | #REF!
Fixed Tasks / other task | [5 empty] | MLS | [5 empty] | SPM |  |  |  | SK
[6 empty] | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site | On-site | Off-site
1 |  | Monthly Deliverables Planning with DDT-ME (Including Click up Updation) |  |  |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 | 3 |  |  | 0 | 2
2 |  | Monthly Review PPT |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 3
3 |  | Invoice |  |  |  | 0 | 0 |  |  |  |  | 0 | 0.5 |  |  | 0 | 0.5 |  |  | 0 | 1.5
4 |  | MCTC |  |  |  | 0 | 0 |  |  |  |  | 0 | 0.5 |  |  | 0 | 0.5 |  |  | 0 | 0.5
5 |  | RC7 (Including Realignment of Deliverables) (0.5 * 8) |  |  |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 1
6 |  | Fortnightly and Monthly Review with Internal team - QA&QC (Including Preparation time) |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
7 |  | Agenda and Action Plan Preparation for visits (6*0.25) and (6*1) |  |  |  | 0 | 0 |  |  |  |  | 0 | 1 |  |  | 0 |  |  |  | 0 | 4
8 |  | Daily Mail checking and Click up updation Activity |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0.5 |  |  | 0 | 0.5
9 |  | Review of Master list of Action Plan and take the follow-up for the same and Weekly RYG (4*1.5) |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0.5 |  |  | 0 | 0.5
10 |  | Data Sync |  |  |  | 0 | 0 |  |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0
Total Hours Fix | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 13
Total Man-days Fix | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53333 | 0 | 0 | 0 | 0.66667 | 0 | 0 | 0 | 1.7333
Total BMD Man Days Fix | [5 empty] | 0 |  | 0 |  | 0 |  | 0.53333 |  | 0 |  | 0.66667 |  | 0 |  | 1.7333
Grand Total Hours | [5 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 41.5 | 13 | 0 | 0 | 60 | 41 | 0 | 0 | #REF! | #REF!
Grand Total Man-days | [5 empty] | 0.5 | 0 | 0 | 0 | 0 | 0 | 6.9167 | 1.7333 | 0 | 0 | 10 | 5.4667 | 0 | 0 | #REF! | #REF!
Grand Total BMD Man Days | [5 empty] | 0.5 |  | 0 |  | 0 |  | 8.65 |  | 0 |  | 15.4667 |  | 0 |  | #REF!
Other Company Man Days | [19 empty] | 0 | 0
Other Company's Total Man Days | [19 empty] | 0
Total Man Days | [5 empty] | 0.5 |  | 0 |  | 0 |  | 8.65 |  | 0 |  | 15.4667 |  | 0 |  | #REF!
Total Available Man Days | [5 empty] | 24 |  |  |  | 25 |  | 24 |  | 25 |  | 24 |  | 25 |  | 21
Total Planned Leave | [7 empty] | 21 |  | 21 |  |  |  | 21 |  |  |  | 21 |  | 21
Total buffer Man Days | [5 empty] | 23.5 |  | -21 |  | 4 |  | 15.35 |  | 4 |  | 8.5333 |  | 4 |  | #REF!
Note on Q47: Shashank: 2 Days - Shrenik Audit 2 Days - Labtech